- Prerequisites:

Source Database Configuration:

Enable Binary Logging:

- log_bin = ON

- binlog_format = ROW

- binlog_row_image = FULL

- server_id configured

- User Permissions

Migration user requires:

- SELECT

- REPLICATION CLIENT

- REPLICATION SLAVE

Network Requirements:

- DMS can access EC2 MySQL.

- DMS can access RDS MySQL.

- Security Groups allow port 3306.

- Migration Strategy:

Phase 1: Environment Preparation

Activities:

- Provision Amazon RDS MySQL.

- Create DMS Replication Instance.

- Configure Security Groups.

- Configure Route Tables if required.

- Create DMS Endpoints.

- Verify connectivity.

Deliverable:

Environment readiness sign-off.

Phase 2: Full Load Migration

Activities:

- Create a DMS Migration Task.

- Select Full Load + CDC mode.

- Start migration.

- Monitor progress.

Expected Outcome:

- All existing tables copied to RDS.

Deliverable:

Full Load Completion Report.

Phase 3: CDC Synchronization

Activities:

- Enable ongoing replication.

- Capture Inserts.

- Capture Updates.

- Capture Deletes.

Expected Outcome:

- Target remains synchronized with source.

Deliverable:

CDC Validation Report.

Phase 4: Data Validation

Validation Activities:

- Record Count Validation: Compare row counts between source and target.

- Sample Data Validation: Validate critical tables.

- Business Validation: Validate:

- Customer Data

- Account Data

- Transaction Data

- Reference Tables

Deliverable:

Migration Validation Report.

Phase 5: Cutover

Pre-Cutover

- Inform stakeholders.

- Schedule maintenance window.

- Take database backup.

- Verify CDC latency.

Cutover Steps

- Stop application writes.

- Allow CDC to catch up.

- Confirm replication latency = 0.

- Stop the DMS task.

- Update application connection string.

- Redirect application to RDS.

- Perform smoke testing.

Deliverable:

Production Cutover Sign-Off.

- Rollback Plan:

Rollback will be initiated if:

- Critical validation failures occur.

- Application connectivity issues persist.

- Data inconsistency is detected.

Rollback Steps:

- Stop application.

- Revert connection string to EC2 MySQL.

- Restart application.

- Notify stakeholders.

- Investigate migration issues.

Expected Recovery Time:

Less than 30 minutes.

- Risk Assessment:

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Network Connectivity Failure | High | Pre-migration connectivity testing |
| DMS Replication Failure | High | Continuous monitoring |
| Data Mismatch | High | Validation procedures |
| Application Connection Issues | Medium | Pre-cutover testing |
| Performance Degradation | Medium | Performance benchmarking |

- Monitoring Plan:

AWS DMS Metrics:

Monitor:

- Full Load Progress

- CDC Source Latency

- CDC Target Latency

- Task Status

- Replication Errors

Database Monitoring

Monitor:

- CPU Utilization

- Memory Usage

- Connections

- Storage Usage

- Slow Queries

- Success Criteria:

Migration will be considered successful when:

- All databases migrated.

- All tables migrated.

- Data validation completed successfully.

- Application functions correctly on RDS.

- No critical defects identified.

- Stakeholder approval obtained.

- Migration Timeline:

| Phase | Duration |
| --- | --- |
| Environment Setup | 1 Day |
| DMS Configuration | 0.5 Day |
| Full Load Migration | Depends on Data Volume |
| CDC Synchronization | 1–7 Days |
| Validation | 1 Day |
| Cutover | 1 Hour |
| Post-Migration Support | 3 Days |

- Deliverables:

- Migration Architecture Document

- Migration Plan

- DMS Configuration Document

- Validation Report

- Cutover Checklist

- Rollback Plan

- Migration Completion Report